| March 2017 | April 2017 | May 2017 | June 2017 | July 2017 | August 2017 | September 2017 | October 2017 | December 2017 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2nd EECERA proposals |  |  | 31st Financial Reporting 4 |  | 30th – 2nd EECERA Conference |  | 31st ToWe final version of materials |  |
| 3rd Book identifying contributors |  | 31st Book completed contributions |  | 24th Final draft to editor |  | 31st Completed book to publishers |  |  |
| 20th – 24th Job Shadowing in Kingston 24th reflection 1-3 pm KU | 24th – 28th Job Shadowing in Barcelona 28th reflection 1-3pm URL | 8th – 12th Job Shadowing in Sandnes 12th reflection 1 – 3pm UiS | TBC Focus Group 3 |  |  | Local Practitioner Workshop | Local Practitioner Workshop | Local Practitioner Workshop |
| EEL visits to settings and Job Shadowing reflection | EEL visits to settings and Job Shadowing reflection | EEL visits to settings and Job Shadowing reflection |  |  |  |  |  |  |
| January 2018 | February 2018 | March 2018 | May 2018 | June 2018 | July 2018 | August 2018 | September 2018 | October 2018 |
| 31st Financial Reporting 5 |  | Book for International Workshop |  |  |  |  | 30th Financial Reporting 6 |  |
| Local Practitioner Workshop | Local Practitioner Workshop | 13th – 14th Transnational Meeting 4 M4 |  |  | 30th Input into report |  | 30th Input into report | 30th Final Report |
|  |  | 15th – 16th International Workshop E1 |  |  |  |  |  |  |